## Feuil1
Role | Objective | Responsibilities | Role KPIs | Who has that role in the project?
Manufacturing Management | Align the project with company objectives | Ensure project team has resources Exercise leadership and ensures the project is well communicated on the factory floor Communicate news of the project to everyone in the factory | All manufacturing KPIs that are affected by the robotic cell project
Project Leader | Define the project's scope and requirements | Define which manual cell to automate and why Define which metrics should be improved Define the cell's target specifications Define the minimum viable cell Monitor the cell's productivity once in production | Robotic cell KPIs (when operating)
Project Coordinator | Ensure the project is done on spec, on time, and on budget | Manage use of project resources Facilitate communication between the project team and other teams in the factory Schedule the different phases of integration | Budget and expenses Project schedule Project definition (is met, is not met)
Engineer | Design a robotic cell that will meet requirements | Document the current manual process and constraints Develop robotic cell concepts Calculate ROI Design the cell List materials needed to build the cell and their cost Test and prototype Document final cell Develop training material for operation and maintenance workers | Requirements of robotic cell Engineering schedule and budget
Installer | Assemble the robotic cell components together | Assemble the (initially) freestanding robotic cell Perform mechanical and electrical installation Install the robotic cell on the production line | Cell is fully installed cell and ready for programming (yes/no) Installation schedule and budget
Programmer | Program the robot to perform as intended | Program the robot Ensure program meets standards for clarity and readability Define levels of access to the robot's program (who can modify what) Interface the communication between the robotic cell and other machines Provide documentation for the program Back up the system | Performance and reliability of program Programming schedule and budget
Operation and maintenance worker | Operate and maintain a productive robotic cell | Start the robot Troubleshoot whenever the cell stops working Keep a log of problems and solutions, and provide feedback to rest of team Bring unresolved problems to the attention of robotic cell project leader Carry out preventive and reactive maintenance tasks | Productivity of robot cell
Process advisor | Ensure the robotic cell process meets or exceeds quality standards | Advise the robotic cell designer and programmer on the process done at the cell | Process quality measures
Procurement | Purchase the right equipment when needed | Purchase robotic cell equipment Ensure purchases are received on time and stored properly | The right equipment is received on time for the right price (yes/no)
Continuous improvement | Improve the robotic cell in time | Identify how the robotic cells could be improved Coordinate continuous improvement projects | KPIs that are targeted for improvement