## Team Roles & Responsibilities
Role | Objective | Responsibilities | Key Performance Indicators (KPIs) | Who Has That Role in the Project?
Manufacturing Manager | Align the project with the company's objectives. | • Provide project team with necessary resources • Exercise leadership to keep the team on track • Communicate news of the project to everyone in the factory | • All manufacturing KPIs that are affected by the robotic cell project
Project Leader | Define the scope and requirements of the project. | • Define which manual cell to automate • Define why there is a need for automation • Define which metrics should be improved • Define the cell's target specifications • Define the minimum viable cell • Monitor the cell's productivity once in operation | • Robotic cell's KPIs (when operating)
Project Coordinator | Ensure the project is carried out according to the specifications, timeline and budget. | • Manage use of project resources • Facilitate communication between the project team and other teams in the factory • Schedule the different phases of integration | • Budget and expenses • Project schedule • Project targets (are met, are not met)
Engineer | Design a robotic cell that will meet the requirements. | • Document the current manual process and constraints • Develop robotic cell concepts • Calculate ROI • Design the cell • List the materials needed to build the cell and their cost • Test and prototype • Document the final cell • Develop training material for operation and maintenance workers | • Requirements of robotic cell • Engineering schedule and budget
Installer | Assemble the robotic cell components. | • Assemble the (initially) freestanding robotic cell • Perform mechanical and electrical installation • Install the robotic cell on the production line | • Cell is fully installed and ready for programming (yes/no) • Installation schedule and budget
Programmer | Program the robot to perform as intended. | • Program the robot • Ensure program meets standards for clarity and readability • Define levels of access to the robot's program (who can modify what) • Set up the interface between the robotic cell and other machines so they can communicate • Provide documentation for the program • Back up the system | • Performance and reliability of program • Programming schedule and budget
Operation and Maintenance Worker | Operate and maintain a productive robotic cell. | • Start the robot • Troubleshoot whenever the cell stops working • Keep a log of problems and solutions, and provide feedback to the rest of the team • Bring unresolved problems to the attention of robotic cell project leader • Carry out preventive and reactive maintenance tasks | • Productivity of robot cell
Process Advisor | Ensure the robotic cell process meets or exceeds quality standards. | • Advise the robotic cell designer and programmer on the process performed at the cell | • Process quality measures
Procurement | Purchase the right equipment when needed. | • Purchase robotic cell equipment • Ensure equipment is received on time and stored properly | • Equipment is received on time for the right price (yes/no)
Continuous Improvement | Improve the robotic cell in time. | • Identify how the robotic cells could be improved • Coordinate continuous improvement projects | • All KPIs targeted for improvement

## Team Skills
PROJECT MANAGEMENT SKILLS | With This Skill You Can... | Who On the Team Has This Skill? | How Critical Is It to Our Robotics Success?
Robotic cell deployment project management | • Define a robotic cell deployment project • Assemble and mobilize the team to execute the project succesfully
DESIGN SKILLS | With This Skill You Can... | Who On the Team Has This Skill? | How Critical Is It to Our Robotics Success?
Manual task mapping | • Document how a manual process is currently performed with the information that will be needed to design the robotic cell
Robotic cell concept | Develop a high-level robotic cell concept • Layout • Choice of components • Operation sequence (outfeed, infeed, process)
Robotic task mapping | • Document how a given process will be performed with a robotic cell.
Manual-to-Robotic gap analysis | • Compare the manual cell map with the robotic cell map • Identify the modifications that will be needed upstream and downstream from the cell • Identify modifications in information transmision when going from manual to robotic
Robotic cell design | Perform the robotic cell engineering work: • Mechanical drawings (custom looting, enclosures, part infeed, outfeed, etc.) • Electrical plans • Control architecture • Prototyping, proofs of concept
Robotic cell safety | • Perform a safety risk assessment • Elaborate strategies to reduce the risk to an appropriate level
INTEGRATE SKILLS | With This Skill You Can... | Who On the Team Has This Skill? | How Critical Is It to Our Robotics Success?
Mechanical installation | • Assemble the robotic cell components following the design instructions
Electrical installation | • Assemble the robotic cell components following the design instructions
Industrial communication | • Interface different machines and sensors so they can communicate with one another
Programming | • Robot instructions • Logic programming
Process | • Adapt a manual process so it can be done by a robot
OPERATE SKILLS | With This Skill You Can... | Who On the Team Has This Skill? | How Critical Is It to Our Robotics Success?
Troubleshooting | • Identify what the problem is in the robotic cell and solve it
Maintenance | • Replace weary components
Optimization | • Improve the cell continuously to increase its productivity